## Start Here
Contractor Job Costing & Estimate Spreadsheet
Estimate → schedule → track hours and costs → change orders → invoice → collect → see real profit. Works in Microsoft Excel (2016+, 365, Mac) and Google Sheets. Version 1.0 (2026-09).
HOW IT FLOWS
1 Settings | 2 Clients, Vendors & Crew | 3 Jobs | 4 Estimate → Proposal | 5 Schedule | 6 Timesheet, Costs, Mileage, Log | 7 Change Orders | 8 Invoices → Payments
Dashboard, Job Profit Report, Reports, Tax Summary and Health Check update themselves from these inputs.
SETUP
Settings | Company details, markups, tax, deposit and progress %, mileage rate, labor burden, cost codes, document text. Start here.
Clients | Client directory with lifetime value and balance due.
Vendors & Crew | Crew rates for the Timesheet; vendor and sub directory with insurance alerts and 1099 flags.
Cost Library | Your price book: items with unit and unit cost that fill into estimates.
INPUTS
Jobs | One row per job. Everything rolls up here.
Estimate | Line-by-line quote with automatic category markup and library lookups.
Schedule | Tasks with workday end dates and a 12-week Gantt chart.
Timesheet | Crew hours by day and job with a weekly payroll summary.
Job Costs | Materials, subs, equipment, permits and other actual costs.
Mileage | Job-related driving at your mileage rate.
Daily Log | Weather, crew, work performed, issues, inspections — your dispute record.
Change Orders | Added work; approved COs raise the contract and the budget.
Invoices | Invoices with balances, status, days overdue and aging bucket.
Payments | Money received, linked to invoices and jobs.
DOCUMENTS & REPORTS
Proposal | Client-ready proposal: scope, payment schedule, detailed lines, terms, signatures.
CO Form | Signature-ready change order document.
Invoice Print | Printable invoice with contract summary.
Client Statement | All of a client's invoices, balances and aging on one page.
Job Profit Report | Budget vs actual by category and cost code for one job.
Reports | Receivables aging, cash forecast, pipeline, win rate, cost-code performance.
Tax Summary | Year-end totals by category, mileage, 1099 review list.
Dashboard | 16 KPIs, alerts, charts, per-job table, monthly P&L.
Health Check | Counts data problems and formula errors. Keep it at ALL CLEAR.
TEN-MINUTE SETUP
1. Settings: company details, markups, contingency, tax, deposit %, mileage rate, labor burden. Rename cost codes to match your trade.
2. Vendors & Crew: add your workers with cost and bill rates, and your subs and suppliers.
3. Clients and Jobs: add a client, then a job row with a Job ID such as J-1001 (the sheet suggests the next one).
4. Estimate the job, open Proposal, pick the Job ID, print. Enter the signed Contract Value on Jobs.
5. As work happens: Timesheet for crew hours, Job Costs for everything else, Mileage, Daily Log, Change Orders.
6. Invoice from the Invoices sheet and print with Invoice Print; record Payments; send Client Statements. Watch the Dashboard.
COLOR KEY
Light-blue cells are inputs. Every other cell is a formula: do not type over them (Undo with Ctrl+Z / Cmd+Z if you do).
Red = over budget, overdue, late, expired, or a data problem. Yellow = watch. Green = on track / paid / done.
PROTECT AGAINST ACCIDENTS (optional)
Input cells are already unlocked. On any sheet, Review → Protect Sheet (leave the password blank) and only the light-blue cells stay editable. Unprotect before inserting rows.
GOOGLE SHEETS
Upload the .xlsx to Google Drive, open it, then File → Save as Google Sheets. Formulas, dropdowns, conditional formatting and the Gantt chart carry over. The three bar charts may need a one-time reformat.
CAPACITY
40 jobs · 400 estimate lines · 1000 timesheet rows · 1000 cost entries · 300 mileage rows · 300 daily-log rows · 100 change orders · 200 invoices · 300 payments · 200 schedule tasks · 100 clients · 30 crew · 100 vendors · 200 library items.
Need more rows? Insert them inside a table (above the TOTAL row), then copy the formula cells of the row above into the new rows.
IMPORTANT
This is an organizational and estimating tool, not accounting, tax, legal or financial advice. Verify figures before quoting, invoicing or filing.
Amounts are formatted in US dollars; change the number format (Format Cells) to use another currency symbol.
Licensed for use in your own business on any number of your devices. Resale or redistribution of the template is not permitted.

## Dashboard
Dashboard
Company-wide view. Everything here is calculated. Change the reporting year in Settings to move the monthly P&L. | [9 empty] | As of
| Revised contract value (all jobs) |  |  | Estimated cost |  |  | Actual cost to date |  |  | Projected gross profit
| Projected gross margin |  |  | Margin after overhead (Settings %) |  |  | Invoiced |  |  | Collected
| Outstanding balance |  |  | Overdue balance |  |  | Backlog (active jobs not yet invoiced) |  |  | Unpaid bills logged (Paid? = No)
| Active jobs (Approved / In Progress) |  |  | Jobs over budget |  |  | Labor hours this month |  |  | Win rate (won ÷ won + lost)
ALERTS
| Overdue invoices |  |  | Late schedule tasks |  |  | Vendor insurance expired / expiring |  |  | Data issues (Health Check)
THIS MONTH
| Invoiced this month |  |  | Collected this month |  |  | Costs this month (all sources) |  |  | Cash profit this month
Charts
Jobs
| Job ID | Client | Status | Revised Contract | Actual Cost | Projected Profit | Margin % | % Budget Used | Balance Due | Days to Target | Hours
| Monthly P&L |  | Year:
| Month | Invoiced | Payments Received | Costs (all sources) | Cash Profit | Cumulative | Labor Hours
TOTAL

## Settings
Settings
Light-blue cells are inputs. Everything here feeds dropdowns, markups, documents and reports on the other sheets.
Company & defaults | Value |  | Code | Cost code name | Category | Job status | Units | Payment methods | Vendor types
Company name | Northline Remodeling LLC |  | 01 | General conditions / supervision | Labor | Lead | ea | Check | Subcontractor
Address | 410 Harbor Rd, Dover, DE 19901 |  | 02 | Demolition & disposal | Labor | Quoted | hr | ACH / Bank | Supplier
Phone / email | (555) 010-2200 · office@northline.example |  | 03 | Site work & excavation | Subcontractor | Approved | day | Card | Equipment rental
License # | DE-HIC-2026-0417 |  | 04 | Concrete & foundation | Subcontractor | In Progress | sq ft | Cash | Other
Default contingency % | 5% |  | 05 | Framing labor | Labor | Complete | lin ft | Zelle
Sales tax % | 0% |  | 06 | Lumber & framing materials | Material | Closed | sq yd | Other
Deposit % of proposal total | 30% |  | 07 | Roofing | Subcontractor | Lost | cu yd
Progress payment % (mid-job) | 40% |  | 08 | Windows & doors | Material |  | gal
Overdue grace (days past due) | 0 |  | 09 | Exterior finishes / siding | Subcontractor |  | box
Reporting / tax year | 2026 |  | 10 | Plumbing | Subcontractor |  | lot
Mileage rate ($ per mile) | 0.7 | Check the current IRS standard mileage rate each January. | 11 | Electrical | Subcontractor
Proposal valid for (days) | 30 |  | 12 | HVAC | Subcontractor
Overhead % of revenue (for net margin) | 10% | Used for 'margin after overhead' on the Dashboard and Job Profit Report. | 13 | Insulation & drywall | Subcontractor
Labor burden % (payroll taxes, insurance, added to crew cost) | 12% | Applied on the Timesheet: Labor cost = hours × rate × (1 + burden). | 14 | Interior finish labor | Labor
Sales tax applies to | Material only | Material only = tax on Material lines. All lines = tax on the whole subtotal. | 15 | Paint & wall finishes | Material
|  |  | 16 | Flooring & tile | Material
Cost category | Default markup % |  | 17 | Cabinets & countertops | Material
Labor | 35% |  | 18 | Fixtures & appliances | Material
Material | 20% |  | 19 | Equipment rental | Equipment
Subcontractor | 15% |  | 20 | Permits & inspections | Permit/Fee
Equipment | 15% |  | 21 | Dumpster & cleanup | Other
Permit/Fee | 0% |  | 22 | Fuel & mileage | Other
Other | 10% |  | 23 | Warranty / callbacks | Labor
Markup is applied to cost: Price = Cost × (1 + markup). Override per line on the Estimate. |  |  | 24 | Miscellaneous | Other
Document text | Value
Proposal terms | This proposal is valid until the date shown. Work begins on receipt of the deposit. Changes to scope are priced as written change orders before work proceeds. Balance is due on completion.
Invoice payment instructions | Pay by check to the company name above, or by bank transfer. Please reference the invoice number.
Invoice / statement footer | Thank you for your business.
Change order terms | The client authorizes the added work and price above. The revised contract total and any schedule change apply from the date signed.
Proposal exclusions & assumptions | Excludes permits not listed, hazardous-material remediation, structural repairs discovered after demolition, and work outside the described scope. Pricing assumes access to water and power on site.
Logo: on Proposal, Invoice Print, CO Form or Client Statement use Insert → Pictures and place it top-right.

## Clients
Clients
One row per client. Jobs, contract value, collected and balance due are calculated from the Jobs sheet. Print a statement from the Client Statement sheet.
Client | Contact person | Phone | Email | Billing address | Notes | Jobs | Contract value (all jobs) | Collected | Balance due | Check
Alvarez residence | Maria Alvarez | (555) 201-7788 | maria.alvarez@example.com | 118 Maple St, Dover, DE 19901
Kim & Patel | Daniel Kim | (555) 318-4402 | dkim@example.com | 42 Orchard Ave, Dover, DE 19904 | Referred by Alvarez
Riverside HOA | L. Chen (board treasurer) | (555) 555-0190 | treasurer@riversidehoa.example | 1 Riverside Dr, Dover, DE 19901 | Net-30 terms

## Vendors & Crew
Vendors & Crew
Crew (your workers, with cost and bill rates) feeds the Timesheet. Vendors & subs feed Job Costs, insurance alerts and the 1099 review.
CREW
Worker | Role | Cost Rate ($/hr) | Bill Rate ($/hr) | Phone | Hours YTD | Labor Cost YTD | Check | Notes
M. Ortiz | Lead carpenter | 42 | 65 | (555) 400-1001
D. Lee | Carpenter | 38 | 55 | (555) 400-1002
S. Reyes | Apprentice | 24 | 40 | (555) 400-1003
J. Owner | Owner / PM | 65 | 85 | (555) 010-2200
VENDORS & SUBCONTRACTORS
Vendor / Sub | Type | Trade | Phone | Email | License # | Insurance Expiry | Insurance Status | W-9 on file | 1099-eligible | Paid YTD | Unpaid Balance | 1099 Flag | Check | Notes
Bright Plumbing | Subcontractor | Plumbing | (555) 600-2001 | office@brightplumbing.example | PL-2231 | 2027-03-01 |  | Yes | Yes
Volt Electric | Subcontractor | Electrical | (555) 600-2002 | jobs@voltelectric.example | EL-8810 | 2026-09-20 |  | Yes | Yes
Smooth Drywall | Subcontractor | Drywall | (555) 600-2003 |  |  | 2026-06-30 |  | Yes | Yes
Stone & Co | Subcontractor | Countertops | (555) 600-2004 |  |  | 2027-01-15 |  | No | Yes
Builders Supply | Supplier | Lumber & hardware | (555) 600-3001 |  |  |  |  | No | No
Tile Outlet | Supplier | Tile | (555) 600-3002 |  |  |  |  | No | No
CabinetDirect | Supplier | Cabinets | (555) 600-3003 |  |  |  |  | No | No
Fixture Depot | Supplier | Plumbing fixtures | (555) 600-3004 |  |  |  |  | No | No
Paint Pro | Supplier | Paint | (555) 600-3005 |  |  |  |  | No | No
Metro Dumpster | Other | Waste | (555) 600-4001 |  |  | 2027-05-31 |  | Yes | No
City of Dover | Other | Permits | (555) 736-7000 |  |  |  |  | No | No
1099 flag is informational only (US vendors paid $600+ in the year and marked eligible). Confirm requirements with your tax professional.
Formulas:
Check = IF([Worker]="","",IF([Labor Cost YTD]="","No expiry on file",IF([Labor Cost YTD]<TODAY(),"EXPIRED",IF([Labor Cost YTD]-TODAY()<=30,"Expiring soon","OK"))))

## Cost Library
Cost Library (price book)
Save the items you estimate repeatedly. On the Estimate sheet, pick a Library Item and the unit and unit cost fill in unless you type your own.
Item | Cost Code | Unit | Unit Cost | Category | Used in estimates | Notes
Demolition — kitchen (per lot) | 02 | lot | 1800
Demolition — bathroom (per lot) | 02 | lot | 900
Framing labor | 05 | hr | 55
Finish carpentry labor | 14 | hr | 55
Paint labor | 14 | hr | 50
Project supervision | 01 | hr | 65
Porcelain tile (material) | 16 | sq ft | 6.5
Quartz countertop installed | 17 | sq ft | 85
Building permit | 20 | ea | 450
Dumpster pull (20 yd) | 21 | ea | 425
Composite decking package | 06 | lot | 7400
Auger / lift rental (day) | 19 | day | 240

## Jobs
Jobs
One row per job. Costs, hours, invoices and payments flow in from the other sheets. Contract Value is optional: leave blank to use the Estimate Price.
Job ID | Client | Job address / description | Status | Start date | Target end | % Complete (manual) | Estimate Price | Contract Value (signed) | Approved Change Orders | Revised Contract | Estimated Cost | Actual Cost to Date | Cost Variance | % of Budget Used | Labor Hours | Invoiced | Collected | Balance Due | Projected Gross Profit | Projected Margin % | Estimated Margin % | Days to Target | Check | Notes
J-1001 | Alvarez residence | Kitchen remodel — 118 Maple St | In Progress | 2026-07-06 | 2026-09-11 | 60% |  | 42500
J-1002 | Kim & Patel | Bathroom remodel — 42 Orchard Ave | Complete | 2026-06-01 | 2026-06-26 | 100%
J-1003 | Riverside HOA | Deck rebuild — clubhouse | Quoted | 2026-09-15 | 2026-10-02 | 0%
J-1004 | Kim & Patel | Basement office build-out | Lost | 2026-08-03 |  | 0%
TOTAL
Formulas:
Days to Target = IF(OR([Job ID]="",[Target end]="",[Status]="Complete",[Status]="Closed",[Status]="Lost"),"",[Target end]-TODAY())

## Estimate
Estimate
One line per item. Pick a Cost Code (drives category and markup) and optionally a Library Item (fills unit and unit cost unless you type your own).
Job ID | Cost Code | Library Item | Description | Qty | Unit | Unit Cost | Category | Unit Cost Used | Unit Used | Est. Cost | Markup Override | Price to Client | Markup Used | Proposal Line # | Check | Notes
J-1001 | 02 | Demolition — kitchen (per lot) |  | 1
J-1001 | 06 |  | Framing lumber & blocking | 1 | lot | 950
J-1001 | 05 | Framing labor |  | 24
J-1001 | 10 |  | Plumbing rough & finish (sub) | 1 | lot | 4200
J-1001 | 11 |  | Electrical rough & finish (sub) | 1 | lot | 3900
J-1001 | 13 |  | Drywall patch & finish (sub) | 1 | lot | 1600
J-1001 | 17 |  | Cabinets | 1 | lot | 9800
J-1001 | 17 | Quartz countertop installed |  | 48
J-1001 | 16 | Porcelain tile (material) | Tile floor material | 220
J-1001 | 14 | Finish carpentry labor | Tile & trim install labor | 40
J-1001 | 15 |  | Paint materials | 1 | lot | 380
J-1001 | 14 | Paint labor |  | 16
J-1001 | 18 |  | Sink, faucet, disposal | 1 | lot | 1150
J-1001 | 20 | Building permit |  | 1
J-1001 | 21 | Dumpster pull (20 yd) | Dumpster (2 pulls) | 2
J-1001 | 01 | Project supervision |  | 30
J-1002 | 02 | Demolition — bathroom (per lot) |  | 1
J-1002 | 10 |  | Plumbing (sub) | 1 | lot | 2600
J-1002 | 11 |  | Electrical (sub) | 1 | lot | 1400
J-1002 | 16 |  | Tile material | 140 | sq ft | 7.25
J-1002 | 14 |  | Tile install labor | 32 | hr | 55
J-1002 | 18 |  | Vanity, toilet, fixtures | 1 | lot | 2100
J-1002 | 15 |  | Paint materials | 1 | lot | 160
J-1002 | 14 |  | Finish carpentry & paint labor | 14 | hr | 50
J-1002 | 20 |  | Permit | 1 | ea | 250
J-1002 | 01 |  | Supervision | 12 | hr | 65
J-1003 | 02 |  | Remove old deck | 1 | lot | 1200
J-1003 | 06 | Composite decking package | PT lumber, composite decking, hardware | 1
J-1003 | 05 |  | Deck framing & decking labor | 90 | hr | 55
J-1003 | 04 |  | Footings (sub) | 1 | lot | 1800
J-1003 | 20 |  | Permit & inspections | 1 | ea | 320
J-1003 | 19 | Auger / lift rental (day) |  | 2
TOTAL (all jobs)

## Proposal
PROPOSAL
[5 empty] | Job ID | J-1001
← pick a job; the proposal at left fills in. Columns H–J never print.
| FROM |  | PREPARED FOR |  | INTERNAL — not printed
Proposal #
| Project |  | Proposal date
Valid until
| Scope summary |  | Price | % of total | Category | Est. Cost | Markup $
| Labor |  |  |  | Labor
| Material |  |  |  | Material
| Subcontractor |  |  |  | Subcontractor
| Equipment |  |  |  | Equipment
| Permit/Fee |  |  |  | Permit/Fee
| Other |  |  |  | Other
| Subtotal |  |  |  | Total cost
| Contingency |  |  |  | Gross margin on subtotal
Gross margin on total
| PROPOSAL TOTAL |  |  |  | Estimate lines for this job
Payment schedule
Deposit at signing
Progress payment (mid-job)
Final payment on completion
# | Detail | Qty | Unit | Line price
Lines shown
Terms
Exclusions & assumptions
Accepted by (client): ______________________________ Date: ____________
For the contractor: _________________________________ Date: ____________

## Schedule
Schedule
Chart start | 2026-07-06 | Legend: | planned | done | today | weekend
Job ID | Task | Assigned to | Start | Duration (workdays) | End | % Complete | Status | Check | Notes
J-1001 | Demolition | M. Ortiz | 2026-07-06 | 2 |  | 100%
J-1001 | Framing & blocking | M. Ortiz | 2026-07-08 | 3 |  | 100%
J-1001 | Rough plumbing (Bright) | J. Owner | 2026-07-13 | 2 |  | 100%
J-1001 | Rough electrical (Volt) | J. Owner | 2026-07-15 | 2 |  | 100%
J-1001 | Rough inspection | J. Owner | 2026-07-17 | 1 |  | 100%
J-1001 | Drywall patch & finish | J. Owner | 2026-07-27 | 4 |  | 100%
J-1001 | Cabinet install | M. Ortiz | 2026-08-04 | 3 |  | 100%
J-1001 | Tile floor | D. Lee | 2026-08-11 | 4 |  | 100%
J-1001 | Countertops (Stone & Co) | J. Owner | 2026-08-18 | 1 |  | 100%
J-1001 | Paint | S. Reyes | 2026-08-24 | 3 |  | 50%
J-1001 | Fixtures, trim & punch list | M. Ortiz | 2026-09-07 | 4 |  | 0%
J-1003 | Remove old deck | D. Lee | 2026-09-15 | 2 |  | 0%
J-1003 | Footings (sub) | J. Owner | 2026-09-17 | 2 |  | 0%
J-1003 | Framing | M. Ortiz | 2026-09-21 | 4 |  | 0%
J-1003 | Decking & rails | M. Ortiz | 2026-09-25 | 3 |  | 0%
J-1003 | Final inspection | J. Owner | 2026-09-30 | 1 |  | 0%

## Timesheet
Timesheet
Crew hours by day and job. Rate Used comes from Vendors & Crew unless you type an override. Log crew labor HERE (or in Job Costs), never both. | [13 empty] | WEEKLY PAYROLL SUMMARY
[14 empty] | Week ending (Sunday) | 2026-07-12 | ← type any Sunday
Date | Worker | Job ID | Cost Code | Hours | Cost Rate Override | Rate Used | Labor Cost (incl. burden) | Bill Rate | Billable Value | Week Ending | Category | Check | Notes | Worker | Hours | Labor cost | Billable | OT hours (>40)
2026-07-07 | M. Ortiz | J-1001 | 02 | 8
2026-07-07 | D. Lee | J-1001 | 02 | 8
2026-07-08 | M. Ortiz | J-1001 | 05 | 8
2026-07-09 | M. Ortiz | J-1001 | 05 | 8
2026-07-09 | D. Lee | J-1001 | 05 | 8
2026-07-10 | D. Lee | J-1001 | 05 | 4
2026-07-11 | D. Lee | J-1001 | 05 | 4 | 57
2026-08-04 | M. Ortiz | J-1001 | 14 | 10
2026-08-05 | M. Ortiz | J-1001 | 14 | 10
2026-08-11 | D. Lee | J-1001 | 14 | 9
2026-08-12 | D. Lee | J-1001 | 14 | 9
2026-08-13 | D. Lee | J-1001 | 14 | 8
2026-08-24 | S. Reyes | J-1001 | 14 | 8
2026-08-25 | S. Reyes | J-1001 | 14 | 8
2026-08-20 | J. Owner | J-1001 | 01 | 22
2026-06-02 | D. Lee | J-1002 | 02 | 10
2026-06-09 | M. Ortiz | J-1002 | 14 | 6
2026-06-10 | M. Ortiz | J-1002 | 14 | 10
2026-06-11 | M. Ortiz | J-1002 | 14 | 10
2026-06-12 | M. Ortiz | J-1002 | 14 | 8
2026-06-15 | M. Ortiz | J-1002 | 14 | 6
2026-06-19 | D. Lee | J-1002 | 14 | 15
2026-06-22 | J. Owner | J-1002 | 01 | 12
TOTAL
TOTAL

## Job Costs
Job Costs (actuals)
Materials, subcontractors, equipment, permits and other real costs. Qty × Unit Cost = Amount. Category comes from the cost code. Crew hours belong on the Timesheet.
Date | Job ID | Cost Code | Category | Vendor | Description | Qty or Hours | Unit Cost / Rate | Amount | Paid? | Payment Method | Receipt / Invoice # | Check | Notes
2026-07-08 | J-1001 | 21 |  | Metro Dumpster | 20 yd dumpster pull 1 | 1 | 425 |  | Yes | Card | MD-4471
2026-07-09 | J-1001 | 06 |  | Builders Supply | Framing lumber & blocking | 1 | 1012.4 |  | Yes | Card | BS-20913
2026-07-14 | J-1001 | 10 |  | Bright Plumbing | Rough-in (50%) | 1 | 2100 |  | Yes | Check | #2201
2026-07-15 | J-1001 | 11 |  | Volt Electric | Rough-in (50%) | 1 | 1950 |  | Yes | Check | #2202
2026-07-21 | J-1001 | 11 |  | Volt Electric | Gas line reroute (CO-1) | 1 | 620 |  | Yes | Check | #2205
2026-07-22 | J-1001 | 20 |  | City of Dover | Building permit | 1 | 450 |  | Yes | Card | P-77120
2026-07-28 | J-1001 | 13 |  | Smooth Drywall | Patch & finish | 1 | 1600 |  | No | Check | INV 1187
2026-08-04 | J-1001 | 17 |  | CabinetDirect | Cabinets delivered | 1 | 9800 |  | Yes | ACH / Bank | CD-55821
2026-08-11 | J-1001 | 16 |  | Tile Outlet | Porcelain tile 230 sq ft | 230 | 6.8 |  | Yes | Card | TO-3310
2026-08-18 | J-1001 | 17 |  | Stone & Co | Quartz tops installed | 1 | 4300 |  | No | Check | SC-0917
2026-08-24 | J-1001 | 11 |  | Volt Electric | Under-cabinet lighting (CO-2) | 1 | 520 |  | No | Check | V-1190
2026-08-25 | J-1001 | 15 |  | Paint Pro | Paint & supplies | 1 | 362.5 |  | Yes | Card | PP-8802
2026-06-03 | J-1002 | 10 |  | Bright Plumbing | Plumbing complete | 1 | 2600 |  | Yes | Check | #2188
2026-06-04 | J-1002 | 11 |  | Volt Electric | Electrical complete | 1 | 1350 |  | Yes | Check | #2189
2026-06-05 | J-1002 | 20 |  | City of Dover | Permit | 1 | 250 |  | Yes | Card | P-76802
2026-06-08 | J-1002 | 06 |  | Builders Supply | Subfloor plywood (CO-4) | 1 | 410 |  | Yes | Card | BS-20640
2026-06-10 | J-1002 | 16 |  | Tile Outlet | Tile 150 sq ft | 150 | 7.1 |  | Yes | Card | TO-3188
2026-06-16 | J-1002 | 18 |  | Fixture Depot | Vanity, toilet, faucet | 1 | 2240 |  | Yes | Card | FD-1022
2026-06-18 | J-1002 | 15 |  | Paint Pro | Paint & supplies | 1 | 172 |  | Yes | Card | PP-8710
TOTAL

## Mileage
Mileage log
Job-related driving. Rate comes from Settings. Amount counts toward the job's actual cost under the cost code you pick (default 22 Fuel & mileage).
Date | Job ID | Cost Code | From | To | Purpose | Miles | Rate | Amount | Category | Check | Notes
2026-07-09 | J-1001 | 22 | Shop | Builders Supply → 118 Maple St | Lumber pickup | 24
2026-08-04 | J-1001 | 22 | Shop | 118 Maple St | Cabinet delivery day | 18
2026-06-16 | J-1002 | 22 | Shop | Fixture Depot → 42 Orchard Ave | Fixture pickup | 15
TOTAL

## Daily Log
Daily Log
A dated record per job: weather, crew, work done, problems, inspections. Hours pull from the Timesheet for that date and job. Useful for change-order and delay disputes.
Date | Job ID | Weather | Crew on site | Hours logged (Timesheet) | Work performed | Issues / delays | Inspections / visitors | Check
2026-07-07 | J-1001 | Sunny | 2 |  | Demo complete; cabinets and flooring removed; hauled to dumpster. | Found corroded gas line behind range — flagged for CO.
2026-07-17 | J-1001 | Cloudy | 1 |  | Rough plumbing/electrical inspection. |  | City inspector — rough-in PASSED
2026-08-12 | J-1001 | Rain | 1 |  | Tile floor: 60% laid. | Tile delivery short 10 sq ft; reorder placed.
2026-06-08 | J-1002 | Sunny | 1 |  | Subfloor replaced after rot found (CO-4). | Half day lost to subfloor rot.

## Change Orders
Change Orders
Approved change orders add to the Revised Contract and the job budget. Pending and Rejected are ignored. Print a signature-ready form on the CO Form sheet.
CO # | Job ID | Date | Description | Status | Markup % | Added Cost (budget) | Price to Client | Added Profit | Schedule impact (days) | Client approved date | Check | Notes
1 | J-1001 | 2026-07-20 | Move gas line for range | Approved |  | 900 |  |  | 1 | 2026-07-21
2 | J-1001 | 2026-08-03 | Add under-cabinet lighting | Approved | 25% | 640 |  |  | 0 | 2026-08-04
3 | J-1001 | 2026-08-18 | Upgrade to pot filler | Pending |  | 480 |  |  | 1
4 | J-1002 | 2026-06-08 | Replace subfloor (rot found) | Approved |  | 750 |  |  | 1 | 2026-06-08

## CO Form
CHANGE ORDER
|  |  | CO # | 2
← pick a change order; the form at left fills in. Columns H–I never print.
| CONTRACTOR | CLIENT
Job
Change order date
Description of change
Schedule impact (days)
Revised target completion
Price of this change
Original contract value
Previously approved change orders
Revised contract total after this change
Status
Terms
Client signature: ______________________________ Date: ____________
Contractor signature: __________________________ Date: ____________

## Invoices
Invoices
One row per invoice sent. Paid to Date pulls from Payments by Invoice #. Status and aging use today's date and the grace days in Settings.
Invoice # | Job ID | Invoice Date | Due Date | Amount | Description | Paid to Date | Balance | Status | Days Overdue | Aging Bucket | Check | Client | Stmt Line # | Notes
INV-2026-014 | J-1001 | 2026-07-06 | 2026-07-13 | 12750 | Deposit — kitchen remodel
INV-2026-019 | J-1001 | 2026-08-05 | 2026-08-19 | 15000 | Progress billing 1 — rough-in complete
INV-2026-023 | J-1001 | 2026-08-28 | 2026-09-11 | 8000 | Progress billing 2 — cabinets & tile
INV-2026-009 | J-1002 | 2026-06-01 | 2026-06-08 | 6000 | Deposit — bathroom remodel
INV-2026-012 | J-1002 | 2026-06-24 | 2026-07-08 | 9137.5 | Final — bathroom remodel incl. CO-4
TOTAL
Formulas:
Status = IF([Invoice #]="","",IF([Balance]<=0,"Paid",IF(AND([Due Date]<>"",TODAY()>[Due Date]+Settings!$B13),"Overdue",IF([Paid to Date]>0,"Partial","Open"))))
Days Overdue = IF([Invoice #]="","",IF([Status]="Overdue",TODAY()-[Due Date],0))
Aging Bucket = IF([Invoice #]="","",IF([Balance]<=0,"Paid",IF(OR([Due Date]="",TODAY()<=[Due Date]),"Current",IF(TODAY()-[Due Date]<=30,"1-30",IF(TODAY()-[Due Date]<=60,"31-60",IF(TODAY()-[Due Date]<=90,"61-90","90+"))))))

## Invoice Print
INVOICE
|  |  | Invoice # | INV-2026-023
← pick an invoice; print or save as PDF. Columns H–I never print.
| FROM | BILL TO
Invoice number
Invoice date
Due date
Job
| Description | Amount
Less: payments received on this invoice
BALANCE DUE
Contract summary
Revised contract value
Invoiced to date (all invoices)
Paid to date (all invoices)
Remaining to invoice
Payment instructions
REMITTANCE — detach and return with payment
Payable to
Invoice number
Balance due
| Amount enclosed | $ ______________

## Payments
Payments received
Every client payment. Invoice # links it to an invoice; Job ID drives the job's Collected total and the cash P&L.
Date | Job ID | Invoice # | Amount | Method | Reference / Check # | Check | Notes
2026-07-08 | J-1001 | INV-2026-014 | 12750 | ACH / Bank | Deposit
2026-08-12 | J-1001 | INV-2026-019 | 15000 | Check | #2210
2026-06-03 | J-1002 | INV-2026-009 | 6000 | Zelle | Deposit
2026-07-01 | J-1002 | INV-2026-012 | 9137.5 | Check | #1187
TOTAL

## Client Statement
STATEMENT
[9 empty] | Client | Alvarez residence
← pick a client; print or save as PDF. Columns K–L never print.
| FROM |  |  |  | TO
| Statement date |  |  |  | TOTAL BALANCE DUE
| Invoice # | Job | Invoice date | Due date | Amount | Paid | Balance | Status
Totals
Aging of open balance
| Current | 1-30 days | 31-60 days | 61-90 days | 90+ days
Payment instructions

## Job Profit Report
Job Profit Report — budget vs actual
Pick a Job ID. Budget = estimate lines + approved change-order cost. Actual = Job Costs + Timesheet labor (incl. burden) + Mileage.
| Job ID | J-1001 |  | Revised contract
| Client |  |  | Invoiced / Collected
| Status |  |  | Balance due
| Start → target end |  |  | Projected gross profit / margin
| % complete (manual) |  |  | Overhead allocation / net margin
| Days to target |  |  | Labor hours: estimated / actual
| By category |  | Estimated Cost | Actual Cost | Variance | % Used | Price Quoted | Actual vs Price
Labor
Material
Subcontractor
Equipment
Permit/Fee
Other
Total by category
| Code | Cost code | Estimated Cost | Actual Cost | Variance ($) | Variance (%) | % Used | Status
Approved change orders (added cost)
(Actual on this line = costs logged without a cost code)
TOTAL JOB BUDGET vs ACTUAL
Unpaid bills on this job (Job Costs, Paid? = No)
Pending change orders (price, not yet approved)
Late schedule tasks
Daily log entries

## Reports
Company reports
Receivables aging, cash forecast, pipeline, win rate and cost-code performance across all jobs. All calculated.
RECEIVABLES AGING
| Bucket | Open balance | Invoices
Current
1-30
31-60
61-90
90+
Total open
CASH FORECAST — open invoices by due month
| Month | Due (open balance) | Invoices
Past due
Total
PIPELINE BY STATUS
| Status | Jobs | Revised contract | Balance due | Projected profit
Lead
Quoted
Approved
In Progress
Complete
Closed
Lost
Total
Win rate (won ÷ won + lost)
COST CODE PERFORMANCE — all jobs
| Cost code | Estimated | Actual | Variance | Variance % | Flag
Total

## Tax Summary
Year-end summary (cash basis, informational)
Totals for the reporting year set in Settings. Hand this to your accountant with your bank statements. Not tax advice.
Reporting year
INCOME
Payments received (cash collected)
Invoiced (accrual reference)
JOB COSTS BY CATEGORY (as logged)
| Category | Job Costs | Timesheet labor | Mileage | Total
Labor
Material
Subcontractor
Equipment
Permit/Fee
Other
Total job costs
Gross profit (collected − job costs)
MILEAGE
Business miles logged
Mileage amount at Settings rate
1099 REVIEW (US)
Vendors flagged for 1099 review
Paid YTD uses the reporting year. Flag = marked 1099-eligible and paid $600 or more. Confirm with your tax professional.
BY QUARTER
| Quarter | Invoiced | Collected | Job costs | Gross profit (cash)
Q1
Q2
Q3
Q4
Year
1099 REVIEW LIST
| Vendor | Type | Paid YTD | W-9 on file | Flag

## Health Check
Health Check
Data problems that would make reports wrong. Each input sheet has a Check column; this page counts them. Fix anything marked Review.
| Check | Issues | Status | Where to look
DATA INTEGRITY
| Jobs: duplicate IDs, unknown client, missing status |  |  | Jobs → Check column
| Clients: duplicate names |  |  | Clients → Check
| Crew: duplicates, missing cost rate |  |  | Vendors & Crew → Crew table
| Vendors: duplicates |  |  | Vendors & Crew → Vendor table
| Estimate lines: unknown job/code, missing qty or cost |  |  | Estimate → Check
| Schedule tasks: unknown job, missing start/duration |  |  | Schedule → Check
| Timesheet: unknown worker/job, missing hours or date |  |  | Timesheet → Check
| Job Costs: unknown job/code, missing qty, cost or date |  |  | Job Costs → Check
| Mileage: unknown job, missing miles or date |  |  | Mileage → Check
| Daily Log: unknown job, missing date |  |  | Daily Log → Check
| Change Orders: unknown job, duplicate #, missing status/date |  |  | Change Orders → Check
| Invoices: duplicate #, unknown job, missing due date/amount |  |  | Invoices → Check
| Payments: unknown job or invoice #, missing date |  |  | Payments → Check
Total data issues
ATTENTION ITEMS (not errors)
| Jobs over budget |  |  | Job Profit Report
| Invoices overdue |  |  | Invoices / Client Statement
| Schedule tasks late |  |  | Schedule
| Vendors with expired insurance |  |  | Vendors & Crew
| Vendors with insurance expiring within 30 days |  |  | Vendors & Crew
| Approved change orders without client-approved date |  |  | Change Orders
| Unpaid bills logged (count) |  |  | Job Costs → Paid?
| Invoices overpaid (balance below zero) |  |  | Invoices / Payments
FORMULA DIAGNOSTICS (should all be 0)
Formula errors on Jobs
Formula errors on Estimate
Formula errors on Timesheet
Formula errors on Job Costs
Formula errors on Mileage
Formula errors on Daily Log
Formula errors on Change Orders
Formula errors on Invoices
Formula errors on Payments
Formula errors on Schedule
Formula errors on Clients
Formula errors on Vendors & Crew
Formula errors on Cost Library
Formula errors on Proposal
Formula errors on CO Form
Formula errors on Invoice Print
Formula errors on Client Statement
Formula errors on Job Profit Report
Formula errors on Reports
Formula errors on Tax Summary
Formula errors on Dashboard
Total formula errors